## Sheet1
CraneLink AI: A Mobile and Web- Based System for Remote Crane Operations, Real- Time Monitoring, and AI- Driven Safety Insights
Task | Task Name | Task Lead | Start Date | End Date | August |  |  |  | September |  |  |  | October |  |  |  | November |  |  |  | December
ID |  |  |  |  | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
1 | Initiation Phase | All Members | 2025-10-08 | 08/18/2025 | bar: August 2 to August 3
1.1 | Identify System Goals & Analysis | Realista | 2025-10-08 | 2025-12-08 | bar: August 2
1.2 | Gather User & Stakeholder Requirements | Realista & Doylabo | 08/13/2025 | 08/15/2025 | bar: August 2
1.3 | Analyze IoT & AI Integration Needs | Cordero & Talisik | 08/16/2025 | 08/17/2025 | bar: August 2 to August 3
1.4 | Document Functional & Non-Functional Requirements | Realista & Alivio | 08/18/2025 | 08/18/2025 | bar: August 3
2 | Planning Phase | All Members | 08/19/2025 | 08/30/2025 | bar: August 3 to August 4
2.1 | Design IoT- AI System Architecture | Cordero & Talisik | 08/19/2025 | 08/22/2025 | bar: August 3
2.2 | Create Database Schema & DFDs | Cordero | 08/23/2025 | 08/25/2025 | bar: August 3 to August 4
2.3 | Design UI/UX for Web and Mobile | Doylabo | 08/26/2025 | 08/28/2025 | bar: August 4
2.4 | Plan Sensor Hardware Integration | Cordero & Talisik | 08/29/2025 | 08/30/2025 | bar: August 4
3 | Iteration/ Sprint Cycles | All Members | 2025-01-09 | 11/30/2025 | bar: August 4 to November 4
3.1 | Sprint 1 | Alivio & Doylabo | 2025-01-09 | 09/20/2025 | bar: August 4 to September 3
3.1.1 | Develop Web Dashboard & Database Link | Doylabo | 2025-01-09 | 2025-04-09 | bar: August 4 to September 1
3.1.2 | Integrate IoT Sensor Modules | Alivio | 2025-05-09 | 2025-10-09 | bar: August 4 to September 2
3.1.3 | Sprint Review & Retrospective | Alivio & Doylabo | 2025-11-09 | 09/20/2025 | bar: August 4 to September 3
3.2 | Sprint 2 | Realista & Talisik | 09/21/2025 | 10/15/2025 | bar: August 4 to October 2
3.2.1 | Implement AI Safety Assistant | Realista | 09/21/2025 | 09/27/2025 | bar: August 4 to September 4
3.2.2 | Implement AI Load & Stability Prediction | Talisik | 09/28/2025 | 2025-05-10 | bar: August 4 to October 1
3.2.3 | Sprint Review & Retrospective | Realista & Talisik | 2025-06-10 | 10/15/2025 | bar: August 4 to October 2
3.3 | Sprint 3 | Cordero &Tedra | 10/16/2025 | 2025-10-11 | bar: August 4 to November 1
3.3.1 | Implement AI Path Optimization | Tedra | 10/16/2025 | 10/24/2025 | bar: August 4 to October 4
3.3.2 | UI/UX Improvements (Web & Mobile) | Cordero | 10/25/2025 | 2025-01-11 | bar: August 4 to November 1
3.3.3 | Sprint Review & Retrospective | Cordero & Tedra | 2025-02-11 | 2025-10-11 | bar: August 4 to November 3
3.4 | Sprint 4 | All Members | 2025-11-11 | 11/30/2025 | bar: August 4 to December 1
3.4.1 | Final Improvements & Optimization | All Members | 2025-11-11 | 11/22/2025 | bar: August 4 to November 4
3.4.2 | Final Sprint Review & Restrospective | All Members | 11/23/2025 | 11/30/2025 | bar: August 4 to December 1
4 | Testing Phase | All Members | 2025-01-12 | 2025-10-12 | bar: August 4 to December 2
4.1 | Integration Testing | All Members | 2025-01-12 | 2025-02-12 | bar: August 4 to December 1
4.2 | System and Acceptance Testing | All Members | 2025-03-12 | 2025-06-12 | bar: August 4 to December 1
4.3 | Bug Fixing & Optimization | All Members | 2025-07-12 | 2025-10-12 | bar: August 4 to December 2
5 | Deployment Phase | Doylabo & Alivio | 2025-11-12 | 12/17/2025 | bar: August 4 to December 3
5.1 | Deploy to Live Environment | Doylabo & Alivio | 2025-11-12 | 2025-12-12 | bar: August 4 to December 2
5.2 | Final Validation with Stakeholders | Realista & Tedra | 12/13/2025 | 12/15/2025 | bar: August 4 to December 3
5.3 | Launch Live System | Realista | 12/16/2025 | 12/17/2025 | bar: August 4 to December 3
6 | Maintenance Phase | All Members | 12/18/2025 | 12/20/2025 | bar: August 4 to December 3
6.1 | Monitor System Performance | All Members | 12/18/2025 | 12/18/2025 | bar: August 4 to December 3
6.2 | Fix Minor Bugs & Issues | All Members | 12/18/2025 | 12/19/2025 | bar: August 4 to December 3
6.3 | System Documentation Update | All Members | 12/19/2025 | 12/19/2025 | bar: August 4 to December 3
6.4 | Backup & Data Security Check | All Members | 12/19/2025 | 12/20/2025 | bar: August 4 to December 3
Done/ Completed
In Progress
Not Yet Started